## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Milestone 1 | Milestone 1 | US-01 | As a user, I want to submit a question, AI response and optional reference answer for evaluation. | Must | Input module | Bhavya sri | Completed
Milestone 1 | Milestone 1 | US-02 | As a system, I want relevant knowledge retrieved from the reference knowledge base for grounded evaluation. | Must | RAG pipeline | Bhavya sri | Completed
Milestone 1 | Milestone 1 | US-03 | As a developer, I want a defined multi-agent architecture, scoring model and orchestration flow. | Must | System design | Bhavya sri | Completed
Milestone 2 | Milestone 2 | US-04 | As a user, I want a Relevance Judge to score how directly the response addresses the question with reasoning. | Must | US-01, RAG | Bhavya sri | Completed
Milestone 2 | Milestone 2 | US-05 | As a user, I want an Accuracy Judge to check factual correctness using reference or retrieved evidence. | Must | US-02 | Bhavya sri | Completed
Milestone 2 | Milestone 2 | US-06 | As a user, I want unsupported claims to be identified by a Hallucination Detection Agent. | Must | US-02, US-05 | Bhavya sri | Completed
Milestone 3 | Milestone 3 | US-07 | As a user, I want completeness scoring to identify missing aspects of an answer. | Must | Evaluation pipeline | Bhavya sri | Completed
Milestone 3 | Milestone 3 | US-08 | As a user, I want a Verdict Agent to combine dimension scores into Pass, Needs Improvement or Fail. | Must | US-04 to US-07 | Bhavya sri | Completed
Milestone 3 | Milestone 3 | US-09 | As a user, I want a clear per-dimension results interface showing scores, reasoning, findings and verdict. | Must | US-04 to US-08 | Bhavya sri | Completed
Milestone 3 | Milestone 3 | US-10 | As a user, I want to upload a CSV and evaluate multiple question-response pairs automatically. | Must | Evaluation pipeline | Bhavya sri | Completed
Milestone 4 | Milestone 4 | US-11 | As a user, I want dashboard analytics and charts to understand batch evaluation quality. | Must | US-10 | Bhavya sri | Completed
Milestone 4 | Milestone 4 | US-12 | As a user, I want structured batch evaluation results exported as a PDF report. | Must | US-10, US-11 | Bhavya sri | Completed
Milestone 4 | Milestone 4 | US-13 | As a developer, I want end-to-end validation of single and batch evaluation workflows. | Must | All modules | Bhavya sri | Completed
Milestone 4 | Milestone 4 | US-14 | As a stakeholder, I want technical documentation, project report and final demonstration material. | Should | Completed system | Bhavya sri | Completed

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30 | Day 31 | Day 32 | Day 33 | Day 34 | Day 35 | Day 36 | Day 37 | Day 38 | Day 39 | Day 40 | Day 41 | Day 42 | Day 43 | Day 44 | Day 45 | Day 46 | Day 47 | Day 48 | Day 49 | Day 50 | Day 51 | Day 52
US-01 | M1-T01 | Study LLM evaluation, hallucination detection, RAG and evaluation frameworks | 30-Jun-2026 | 02-Jul-2026 | Bhavya sri | Research | Completed | 6 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | M1-T02 | Design architecture, agent responsibilities, scoring dimensions and data model | 01-Jul-2026 | 04-Jul-2026 | Bhavya sri | System Design | Completed | 8 | 0 | 1 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | M1-T03 | Implement initial Evaluation Input Module | 03-Jul-2026 | 06-Jul-2026 | Bhavya sri | Implementation | Completed | 8 | 0 | 0 | 0 | 1 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | M1-T04 | Prepare reference data, chunk content, create embeddings and retrieval index | 04-Jul-2026 | 08-Jul-2026 | Bhavya sri | RAG Development | Completed | 12 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | M1-T05 | Validate retrieval and prepare Milestone 1 submission | 08-Jul-2026 | 09-Jul-2026 | Bhavya sri | Validation | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | M2-T01 | Implement Relevance Judge Agent | 10-Jul-2026 | 14-Jul-2026 | Bhavya sri | Agent Development | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | M2-T02 | Implement Accuracy Judge Agent with supporting evidence | 13-Jul-2026 | 17-Jul-2026 | Bhavya sri | Agent Development | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | M2-T03 | Implement Hallucination Detection Agent | 15-Jul-2026 | 19-Jul-2026 | Bhavya sri | Agent Development | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | M2-T04 | Validate three agents on varied question-answer pairs | 18-Jul-2026 | 21-Jul-2026 | Bhavya sri | Validation | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | M3-T01 | Implement Completeness Judge Agent | 22-Jul-2026 | 25-Jul-2026 | Bhavya sri | Agent Development | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-08 | M3-T02 | Implement Verdict Agent with weighted scoring | 24-Jul-2026 | 28-Jul-2026 | Bhavya sri | Agent Development | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | M3-T03 | Develop per-dimension scoring and reasoning interface | 26-Jul-2026 | 29-Jul-2026 | Bhavya sri | UI Development | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | M3-T04 | Implement CSV batch evaluation and aggregated results | 27-Jul-2026 | 31-Jul-2026 | Bhavya sri | Batch Processing | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | M4-T01 | Build Evaluation Scoring Dashboard and analytics charts | 01-Aug-2026 | 05-Aug-2026 | Bhavya sri | Dashboard | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | M4-T02 | Implement PDF report generation and download | 04-Aug-2026 | 07-Aug-2026 | Bhavya sri | Report Generation | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | M4-T03 | Conduct end-to-end testing for single and batch workflows | 07-Aug-2026 | 11-Aug-2026 | Bhavya sri | Testing | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | M4-T04 | Prepare technical documentation, project report and final demonstration | 09-Aug-2026 | 13-Aug-2026 | Bhavya sri | Documentation | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | M4-T05 | Final refinement of documentation, project report, agile artifacts and demonstration readiness | 14-Aug-2026 | 20-Aug-2026 | Bhavya sri | Finalization | Completed | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 2 | 2 | 2 | 1

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Milestone 1 | 02-Jul-2026 | Architecture and research documents were still being refined while the project structure was evolving. | Consolidated system design, agent responsibilities, data models and technology choices.
Milestone 1 | 03-Jul-2026 | Initial planning artifacts needed alignment with the implementation scope. | Created/updated project plan, data models, agent definitions and technology-stack documentation.
Milestone 1 | 07-Jul-2026 | The initial input module was separate from the final Flask workflow. | Implemented and validated the Evaluation Input Module for question, response and optional reference input.
Milestone 1 | 09-Jul-2026 | The prototype needed a usable web interface for demonstration. | Added the Flask prototype and connected the input workflow to the application.
Milestone 2 | 14-Jul-2026 | Prototype files and the final implementation structure had diverged. | Reorganized the repository into the final source structure.
Milestone 2 | 16-Jul-2026 | Individual judge outputs had to replace placeholder evaluation results. | Integrated Relevance, Accuracy and Hallucination judges through ResponseEvaluator.
Milestone 2 | 18-Jul-2026 | Agent evaluation needed broader validation than individual manual examples. | Started the benchmark validation framework and expanded automated evaluation coverage.
Milestone 2 | 20-Jul-2026 | Benchmark validation required refinement and dataset-processing support. | Refined validation flow and sampling support before milestone completion.
Milestone 3 | 30-Jul-2026 | Validation and reporting requirements were expanding with the evaluation pipeline. | Completed TruthfulQA benchmark support and structured validation outputs.
Milestone 3 | 31-Jul-2026 | Evaluation results needed readable evidence for analysis. | Generated benchmark sample reports and finalized milestone-level evaluation workflow.
Milestone 4 | 05-Aug-2026 | Batch evaluation needed analytics rather than only row-level results. | Integrated batch analytics, verdict distribution and quality-trend presentation.
Milestone 4 | 07-Aug-2026 | Batch results needed a structured export mechanism. | Integrated PDF report generation and report-download support.
Milestone 4 | 11-Aug-2026 | The complete pipeline required systematic functional and error-handling validation. | Ran the end-to-end test suite covering 14 cases.
Milestone 4 | 13-Aug-2026 | Final deliverables had to align with the completed implementation. | Finalized documentation, report material and demonstration-ready outputs.
Milestone 4 | 14-Aug-2026 | Final deliverables required alignment after the main implementation was completed. | Reviewed and refined the technical documentation, project report and Agile documentation.
Milestone 4 | 18-Aug-2026 | Final artifacts required consistency across implementation, screenshots and documentation. | Cross-checked project artifacts, screenshots, repository structure and report content.
Milestone 4 | 20-Aug-2026 | Final submission package required a last consistency check. | Completed final review and prepared the project demonstration/submission package.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Milestone 1 | 30-Jun-2026 | 09-Jul-2026 | Bhavya sri | Validate architecture decisions early with small prototypes. | Avoid overextending research before implementation feedback. | Keep modular agents and RAG grounding central. | Use prototype feedback to refine architecture.
2 | Milestone 2 | 10-Jul-2026 | 21-Jul-2026 | Bhavya sri | Add structured validation cases while building agents. | Avoid testing only ideal responses. | Keep agent outputs explicit and explainable. | Expand evaluation examples across QA types.
3 | Milestone 3 | 22-Jul-2026 | 31-Jul-2026 | Bhavya sri | Design UI and aggregation together for consistency. | Avoid redundant summaries in consolidation. | Separate dimension scores from final verdict. | Keep Verdict Agent responsible for final consolidation.
4 | Milestone 4 | 01-Aug-2026 | 13-Aug-2026 | Bhavya sri | Plan documentation and validation alongside feature work. | Avoid leaving all documentation to the end. | Keep dashboard, reporting and testing aligned with pipeline. | Finalize technical documentation, report and demo materials.

## Defects
Defect ID | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
D-001 | The early Flask workflow used placeholder evaluation values instead of live judge-agent results. | Milestone 2 | Bhavya sri | Integration | Replaced placeholder result dictionaries with the ResponseEvaluator pipeline and connected the Relevance, Accuracy and Hallucination judges. | 16-Jul-2026 | Closed | Repository change replaced placeholder results with evaluator-driven results.
D-002 | The prototype repository structure no longer matched the final project organization. | Milestone 2 | Bhavya sri | Structure / Integration | Reorganized the repository into the final src-based project structure. | 14-Jul-2026 | Closed | Repository history records final source-structure creation and reorganization.
D-003 | LLM judge responses required robust JSON parsing and protection against missing output keys. | Milestone 2 | Bhavya sri | Robustness | Added JSON response parsing and defensive defaults for fields such as unsupported_claims and reasoning. | 16-Jul-2026 | Closed | Agent/evaluator implementation includes parsing and fallback handling.
D-004 | Initial validation coverage was not sufficient for systematic benchmark evaluation. | Milestone 3 | Bhavya sri | Validation | Expanded the benchmark validation framework with TruthfulQA support, sampling modes and generated validation reports. | 30-Jul-2026 | Closed | Repository history shows multiple validation-framework commits from 18–30 Jul.
D-005 | Batch evaluation required a complete presentation and reporting flow rather than only row-level processing. | Milestone 4 | Bhavya sri | Feature Integration | Integrated batch evaluation, analytics, verdict distribution, PDF report generation and report-download support. | 13-Aug-2026 | Closed | Repository commit includes batch_evaluator.py, pdf_report.py, analytics integration and download-report support.

## Unit Test Plan
Sl: No: | Test Case Name | Test Procedure | Condition to be tested | Expected Result | Actual Result
1 | Input validation | Submit valid question and response through the evaluation interface. | Required question and response are provided. | Input is accepted and evaluation starts. | Passed
2 | Empty question handling | Submit an empty question. | Question field is blank. | System handles invalid input without normal evaluation. | Passed
3 | Empty response handling | Submit an empty AI response. | Response field is blank. | System handles invalid input without normal evaluation. | Passed
4 | Reference handling | Run evaluation with and without a reference. | Reference is optional. | Reference is used when supplied; otherwise retrieval can provide grounding evidence. | Passed
5 | Relevance judge | Evaluate a question-response pair for relevance. | Valid question and response are supplied. | Relevance score and reasoning are generated. | Passed
6 | Accuracy judge | Evaluate factual accuracy using available grounding. | Reference or relevant evidence is available. | Accuracy score and supporting evidence are generated. | Passed
7 | Hallucination detection | Evaluate a response containing unsupported information. | Grounding evidence is available. | Unsupported claims are identified and reported. | Passed
8 | Completeness judge | Evaluate a response that omits requested aspects. | Question contains multiple expected aspects. | Completeness score and omissions are generated. | Passed
9 | Verdict aggregation | Run the complete judge pipeline. | Dimension scores are available. | Weighted overall score and final verdict are generated. | Passed
10 | Batch CSV validation | Upload a CSV containing question and response columns. | Required CSV columns are present. | Rows are accepted for batch processing. | Passed
11 | Batch evaluation | Process multiple question-response pairs. | Valid batch dataset is uploaded. | Rows are evaluated and aggregate results are generated. | Passed
12 | Dashboard analytics | Open analytics after batch evaluation. | Batch results are available. | Aggregate cards, charts and verdict distribution are displayed. | Passed
13 | PDF report export | Download the report after a completed batch run. | Batch results are available. | A structured PDF report is generated and downloaded. | Passed
14 | End-to-end pipeline | Execute the complete evaluation workflow. | All modules are available. | Full workflow completes successfully. | Passed